## BPH1 Phase-2_R70.x_Release
R70.x WASND 9.x BPH1 Phase-2 Runsheet (July 2023)

## Pre-Implementation
BPH1 Phase-2 RUN SHEET |  |  | Change : CHG0099204 | VERSION: 1.01
Pre-Implementation Activities | [7 empty] | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites | Pre-requsites
ID | Activity Code | Task Title | Task Description | Duration | Start | Finish | Owner
1 | PT-WASND 9-13 | Create directory | Create a directory tree as below: mkdir -p /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021 | 5min | 26/07/2023 14:00 | 26/07/2023 14:05 | BPHTechnical Support Team
1 | PT-WASND 9-13 | Copy the files to the server | Copy the downloaded files to below locations in the server For BPH1 : DMGR - /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021 BATCH - /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021 RT - /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021 NRT - /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021 | 5min | 26/07/2023 14:05 | 26/07/2023 14:10 | BPHTechnical Support Team
2 | PT-WASND 9-13 | Directory verifications | Make sure that these directories exist: in DMGR, BATCH, RT, NRT 9.0.5-WS-WAS-FP013 WAS_ND_V9.0_MP_ML agent.installer.aix.gtk.ppc_1.9.2001.20211222_1411 ibm-java-sdk-8.0-6.26-aix-ppc64-installmgr ibm-java-sdk-8.0-6.36-aix-ppc64-installmgr Installation Manager 1.9.1.2 | 5min | 26/07/2023 14:10 | 26/07/2023 14:15 | BPHTechnical Support Team

## WASNDBaseVersionInst - DMGR
BPH1 Phase-2 RUN SHEET |  |  | Change :CHG0099204 | VERSION: 1.01
ID | Activity Code | Task Title | Task Description | Duration | Start | Finish | Owner
Pre-requsites
1 | PT-WASND 9-13 | Service account verification | Installation operator to login with newly created service account Login via putty using service account username as wasuadmin | 1 minute | 14:30 | 14:31 | BPHTechnical Support Team
2 | PT-WASND 9-13 | File System Verification | Ensure that filesystems are allocated as requested run the command : df -g /dev/fslv12 60.00 38.07 37% 74609 1% /usr/IBM/WASND_BPH1 | 1 minute | 14:32 | 14:33 | BPHTechnical Support Team
WASND 9.x Installation Steps
3 | Installation Manager 1.9.1.2 | Installation Manager installation | Step1>Install the Installation Manager cd /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/ cd "Installation Manager 1.9.1.2" ./userinstc -installationDirectory /usr/IBM/WASND_BPH1/InstallationManager/ -acceptLicense -sVP | 5 minutes | 14:33 | 14:38 | BPHTechnical Support Team
4 | Installation Manager 1.9.1.2 | Verify Installation Manager installation | Verify the installation manager instaaltion by running the command cd "/usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/Installation Manager 1.9.1.2" ./userinstc -version Installation Manager (install kit) Version: 1.9.2.1 Internal Version: 1.9.2001.20211222_1411 Architecture: 32-bit Installation Manager (installed) Version: 1.9.2.1 Internal Version: 1.9.2001.20211222_1411 Architecture: 32-bit | 1 minute | 14:38 | 14:39 | BPHTechnical Support Team
5 | WASND 9.0 Fixpacks 006 | WASND9 fix pack installation script | Step2>verification of script file to exists as below with appropriate content run the below command cat /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/WASND9FixpackInstaller.sh echo "Installing WAS 9.0 Fixpacks 006" "/usr/IBM/WASND_BPH1/InstallationManager/eclipse/tools/imcl" install com.ibm.websphere.ND.v90_9.0.0.20160526_1854,core.feature,ejbdeploy,embeddablecontainer,thinclient,samples com.ibm.java.jdk.v8_8.0.6026.20210223_0615 -repositories /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/WAS_ND_V9.0_MP_ML,/usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/ibm-java-sdk-8.0-6.26-aix-ppc64-installmgr -installationDirectory /usr/IBM/WASND_BPH1/WebSphere/ProcServer -sharedResourcesDirectory /usr/IBM/WASND_BPH1/IBM/IMShared/ -acceptLicense -log /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/Install_WAS_ND_V9.0_MP_ML.xml -showProgress | 5 minutes | 14:39 | 14:44 | BPHTechnical Support Team
6 | WASND 9.0 Fixpacks 006 | Run the WASND9 fix pack installation script | cd /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/ sh WASND9FixpackInstaller.sh | 10 minutes | 14:44 | 14:54 | BPHTechnical Support Team
7 | WASND 9.0 Fixpacks 006 | Verify the WASND9 fix pack installation | ## After Installation Installed com.ibm.websphere.ND.v90_9.0.0.20160526_1854 to the /usr/IBM/WASND_BPH1/WebSphere/ProcServer directory. Installed com.ibm.java.jdk.v8_8.0.6026.20210223_0615 to the /usr/IBM/WASND_BPH1/WebSphere/ProcServer directory. | 1 minute | 14:54 | 14:55 | BPHTechnical Support Team
8 | JDK fix pack .26 | Install fix pack .26 (java fix pack) - 8.0.6.26 | Step3> verification of script file to exists as below with appropriate content run the below command cat WASND9FixpackInstaller_Fix_9.0.5_FP013.sh "/usr/IBM/WASND_BPH1/InstallationManager/eclipse/tools/imcl" install com.ibm.websphere.ND.v90_9.0.5013.20220815_1557,core.feature,ejbdeploy,embeddablecontainer,thinclient -repositories /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/9.0.5-WS-WAS-FP013,/usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/ibm-java-sdk-8.0-6.36-aix-ppc64-installmgr -installationDirectory /usr/IBM/WASND_BPH1/WebSphere/ProcServer -acceptLicense -log /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/9.0.5-WS-WAS-FP013.xml -showProgress | 5 minutes | 14:55 | 15:00 | BPHTechnical Support Team
9 | JDK fix pack .26 | Install fix pack .26 (java fix pack) - 8.0.6.26 | execution of script for fix pack .26 installation run the script by using the below command cd /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021 sh WASND9FixpackInstaller_Fix_9.0.5_FP013.sh | 10 minutes | 15:00 | 15:10 | BPHTechnical Support Team
10 | JDK fix pack .26 | Verification of fix pack .26 | verification of fix pack .26 installation /usr/IBM/WASND_BPH1/WebSphere/ProcServer/bin$./versionInfo.sh | 1 minute | 15:10 | 15:11 | BPHTechnical Support Team
11 | JDK fix pack .36 | Install fix pack .26 (java fix pack) - 8.0.6.36 | Step3> verification of script file to exists as below with appropriate content run the below command cat WASND9FixpackInstaller_Fix_9.0.5_FP013.sh_whenJava36 echo Installing WAS 9.0.5 Fixpacks 013 "/usr/IBM/WASND_BPH1/InstallationManager/eclipse/tools/imcl" install com.ibm.java.jdk.v8_8.0.6036.20210825_0738 -repositories /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/ibm-java-sdk-8.0-6.36-aix-ppc64-installmgr -installationDirectory /usr/IBM/WASND_BPH1/WebSphere/ProcServer -acceptLicense -log /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/9.0.5-WS-WAS-FP013_java.xml -showProgress | 5 minutes | 15:11 | 15:16 | BPHTechnical Support Team
12 | JDK fix pack .36 | Install fix pack .26 (java fix pack) - 8.0.6.36 | execution of script for fix pack .36 installation run the script by using the below command cd /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021 sh WASND9FixpackInstaller_Fix_9.0.5_FP013.sh_whenJava36 | 10 minutes | 15:16 | 15:26 | BPHTechnical Support Team
13 | JDK fix pack .36 | Verification of fix pack .36 | verification of fix pack .36 installation /usr/IBM/WASND_BPH1/WebSphere/ProcServer/bin$./versionInfo.sh | 1 minute | 15:26 | 15:27 | BPHTechnical Support Team
Application Profile creation Steps
14 | Profile creations | Pre-requisites - I | The below directory structure should exist as below /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES create it by using the below mkdir tree command mkdir -p /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES | 5 minutes | 15:27 | 15:32 | BPHTechnical Support Team
15 | Profile creations | Pre-requisites - II | make sure the below directories exists under the path /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES create them by using the below mkdir command mkdir Cell | 5 minutes | 15:32 | 15:37 | BPHTechnical Support Team
16 | Profile creations | Pre-requisites - III | make sure that appropriate files are copied under Cell directory. Run the below commands cd /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES/Cell ls CellDMGR.props CellPorts.props | 5 minutes | 15:37 | 15:42 | BPHTechnical Support Team
24 | Start DMGR | Script execution forstarting DMGR | Start DMGR | 5 minutes | 15:42 | 15:47 | BPHTechnical Support Team

## WASNDBaseVersionInstall- Nodes
BPH1 Phase-2 RUN SHEET |  |  | Change : CHG0099204 | VERSION: 1.01
ID | Activity Code | Task Title | Task Description | Duration | Start | Finish | Owner
Pre-requsites
1 | PT-WASND 9-13 | Service account verification | Installation operator to login with newly created service account Login via putty using service account username as wasuadmin | 1 minute | 15:50 | 15:51 | BPHTechnical Support Team
2 | PT-WASND 9-13 | File System Verification | Ensure that filesystems are allocated as requested run the command : df -g /dev/fslv12 60.00 38.07 37% 74609 1% /usr/IBM/WASND_BPH1 | 1 minute | 15:51 | 15:52 | BPHTechnical Support Team
WASND 9.x Installation Steps
3 | Installation Manager 1.9.1.2 | Installation Manager installation | Step1>Install the Installation Manager cd /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/ cd "Installation Manager 1.9.1.2" ./userinstc -installationDirectory /usr/IBM/WASND_BPH1/InstallationManager/ -acceptLicense -sVP | 5 minutes | 15:52 | 15:57 | BPHTechnical Support Team
4 | Installation Manager 1.9.1.2 | Verify Installation Manager installation | Verify the installation manager instaaltion by running the command cd "/usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/Installation Manager 1.9.1.2" ./userinstc -version Installation Manager (install kit) Version: 1.9.2.1 Internal Version: 1.9.2001.20211222_1411 Architecture: 32-bit Installation Manager (installed) Version: 1.9.2.1 Internal Version: 1.9.2001.20211222_1411 Architecture: 32-bit | 1 minute | 15:57 | 15:58 | BPHTechnical Support Team
5 | WASND 9.0 Fixpacks 006 | WASND9 fix pack installation script | Step2>verification of script file to exists as below with appropriate content run the below command cat /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/WASND9FixpackInstaller.sh echo "Installing WAS 9.0 Fixpacks 006" "/usr/IBM/WASND_BPH1/InstallationManager/eclipse/tools/imcl" install com.ibm.websphere.ND.v90_9.0.0.20160526_1854,core.feature,ejbdeploy,embeddablecontainer,thinclient,samples com.ibm.java.jdk.v8_8.0.6026.20210223_0615 -repositories /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/WAS_ND_V9.0_MP_ML,/usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/ibm-java-sdk-8.0-6.26-aix-ppc64-installmgr -installationDirectory /usr/IBM/WASND_BPH1/WebSphere/ProcServer -sharedResourcesDirectory /usr/IBM/WASND_BPH1/IBM/IMShared/ -acceptLicense -log /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/Install_WAS_ND_V9.0_MP_ML.xml -showProgress | 5 minutes | 15:58 | 16:03 | BPHTechnical Support Team
6 | WASND 9.0 Fixpacks 006 | Run the WASND9 fix pack installation script | cd /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/ sh WASND9FixpackInstaller.sh | 10 minutes | 16:03 | 16:13 | BPHTechnical Support Team
7 | WASND 9.0 Fixpacks 006 | Verify the WASND9 fix pack installation | ## After Installation Installed com.ibm.websphere.ND.v90_9.0.0.20160526_1854 to the /usr/IBM/WASND_BPH1/WebSphere/ProcServer directory. Installed com.ibm.java.jdk.v8_8.0.6026.20210223_0615 to the /usr/IBM/WASND_BPH1/WebSphere/ProcServer directory. | 1 minute | 16:13 | 16:14 | BPHTechnical Support Team
8 | JDK fix pack .26 | Install fix pack .26 (java fix pack) - 8.0.6.26 | Step3> verification of script file to exists as below with appropriate content run the below command cat WASND9FixpackInstaller_Fix_9.0.5_FP013.sh "/usr/IBM/WASND_BPH1/InstallationManager/eclipse/tools/imcl" install com.ibm.websphere.ND.v90_9.0.5013.20220815_1557,core.feature,ejbdeploy,embeddablecontainer,thinclient -repositories /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/9.0.5-WS-WAS-FP013,/usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/ibm-java-sdk-8.0-6.36-aix-ppc64-installmgr -installationDirectory /usr/IBM/WASND_BPH1/WebSphere/ProcServer -acceptLicense -log /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/9.0.5-WS-WAS-FP013.xml -showProgress | 5 minutes | 16:14 | 16:19 | BPHTechnical Support Team
9 | JDK fix pack .26 | Install fix pack .26 (java fix pack) - 8.0.6.26 | execution of script for fix pack .26 installation run the script by using the below command cd /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021 sh WASND9FixpackInstaller_Fix_9.0.5_FP013.sh | 10 minutes | 16:19 | 16:29 | BPHTechnical Support Team
10 | JDK fix pack .26 | Verification of fix pack .26 | verification of fix pack .26 installation /usr/IBM/WASND_BPH1/WebSphere/ProcServer/bin$./versionInfo.sh | 1 minute | 16:29 | 16:30 | BPHTechnical Support Team
11 | JDK fix pack .36 | Install fix pack .26 (java fix pack) - 8.0.6.36 | Step3> verification of script file to exists as below with appropriate content run the below command cat WASND9FixpackInstaller_Fix_9.0.5_FP013.sh_whenJava36 echo Installing WAS 9.0.5 Fixpacks 013 "/usr/IBM/WASND_BPH1/InstallationManager/eclipse/tools/imcl" install com.ibm.java.jdk.v8_8.0.6036.20210825_0738 -repositories /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/ibm-java-sdk-8.0-6.36-aix-ppc64-installmgr -installationDirectory /usr/IBM/WASND_BPH1/WebSphere/ProcServer -acceptLicense -log /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021/9.0.5-WS-WAS-FP013_java.xml -showProgress | 5 minutes | 16:30 | 16:35 | BPHTechnical Support Team
12 | JDK fix pack .36 | Install fix pack .26 (java fix pack) - 8.0.6.36 | execution of script for fix pack .36 installation run the script by using the below command cd /usr/IBM/WASND_BPH1/Softwares/BPH_Upgrade_2021 sh WASND9FixpackInstaller_Fix_9.0.5_FP013.sh_whenJava36 | 10 minutes | 16:35 | 16:45 | BPHTechnical Support Team
13 | JDK fix pack .36 | Verification of fix pack .36 | verification of fix pack .36 installation /usr/IBM/WASND_BPH1/WebSphere/ProcServer/bin$./versionInfo.sh | 1 minute | 16:45 | 16:46 | BPHTechnical Support Team
Application Profile creation Steps
14 | Profile creations | Pre-requisites - I | The below directory structure should exist as below /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES create it by using the below mkdir tree command mkdir -p /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES | 5 minutes | 16:46 | 16:51 | BPHTechnical Support Team
15 | Profile creations | Pre-requisites - II | make sure the below directories exists under the path /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES create them by using the below mkdir command mkdir Node mkdir NodeAgent | 5 minutes | 16:51 | 16:56 | BPHTechnical Support Team
16 | Profile creations | Pre-requisites - IV | make sure that appropriate files are copied under Node directory. Run the below commands cd /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES/Node ls Node.props NodePorts.props | 5 minutes | 16:56 | 17:01 | BPHTechnical Support Team
17 | Profile creations | Pre-requisites - V | make sure that appropriate files are copied under NodeAgent directory. Run the below commands cd /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES/NodeAgent ls port.props | 5 minutes | 17:01 | 17:06 | BPHTechnical Support Team
18 | Manage Profiles App Node | Script execution for Manage Profiles AppNode | Run the below commands cd ${WAS_HOME}/bin ./manageprofiles.sh -response /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES/Node/Node.props | 15 minutes | 17:06 | 17:21 | BPHTechnical Support Team
19 | Manage Profile App NodeAgent | Script execution for Manage Profile App NodeAgent | Run the below commands cd ${NODE_BIN} ./addNode.sh auggvbpba603 8882 -username admin -password password -profileName WASNDBatchNode01 -portprops /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES/NodeAgent/port.props -includeapps | 15 minutes | 17:21 | 17:36 | BPHTechnical Support Team
20 | Verification of Nadoe Agent status | Verification of Nadoe Agent status | Verification of Nadoe Agent status - node agent is up, Nodes are synced, | 15 minutes | 17:36 | 17:51 | BPHTechnical Support Team
21 | RT | Installation of RT node and profile creations | Repeat Steps from ID3 to ID20 Note: profile Name to be WASNDRTNode01 (ID/Step# 19) | 1 hour | 17:51 | 18:51 | BPHTechnical Support Team
22 | NRT | Installation of NRT node and profile creations | Repeat Steps from ID3 to ID20 Note: profile Name to be WASNDNRTNode01 (ID/Step# 19) | 1 hour | 18:51 | 19:51 | BPHTechnical Support Team
23 | Verification of DMGR, Node Agent | Console Verification | Login to newly created console URL and make sure you are able to see the environmnet Nodes are sunced and up. | 5 minutes | 19:51 | 19:55 | BPHTechnical Support Team

## UpdateBPH1Config
BPH1 Phase-2 RUN SHEET |  |  | Change :CHG0099204 | VERSION: 1.01
ID | Activity Code | Task Title | Task Description | Duration | Start | Finish | Owner
Pre-requsites
1 | PT-WASNDConfig-01 | WASND 9.x.x Installation Status | WASND 9 should be available in the new file system. | 5 min | 20:00 | 20:05 | BPHTechnical Support Team
2 | PT-WASNDConfig-02 | SSL Config creation status | SSL Configuration with Selected cipher as "SSL_RSA_WITH_AES_256_CBC_SHA256" in QoP is already available. | 2 min | 20:05 | 20:07 | BPHTechnical Support Team
WPS Configuration Update
3 | PT-WASNDConfig-03 | Download and extract the attached scripts | Download the BPH1 Configuration scripts from : http://cis.bph1.dev.cba/ivy/built/cba.ph.bwa/scripts/WASND_BPH1_Python.zip | 5 min | 20:07 | 20:12 | BPHTechnical Support Team
4 | PT-WASNDConfig-04 | Verify the files downloaded have required artefacts | Navigate to downloaded compressed folder and extract the WASND_BPH1_Python.zip Uncompress it | 5 min | 20:12 | 20:17 | BPHTechnical Support Team
5 | PT-WASNDConfig-05 | Download all server creation scripts | Make sure the below files are extracted to your local server: config_bph1.properties PHBWAServer01.properties PHGLEventsServer01.properties PHGLSubmitServer01.properties PHPJServer01.properties PHSDEODServer01.properties PHExecutionManager_Cluster.properties PHDEServer_Cluster.properties PHCPLServer_Cluster.properties bph1_sec_creation.py bph1_ssl_cert_maps.py PHSDEODServer01_creation.py PHPJServer01_creation.py PHGLSubmitServer01_creation.py PHGLEventsServer01_creation.py PHBWAServer01_creation.py PHCPLCluster.py PHDECluster.py PHExecutionManagerCluster.py | 1 min | 20:17 | 20:18 | BPHTechnical Support Team
6 | PT-WASNDConfig-06 | Download all property files under scrikpt_properties directory | mkdir -p /usr/IBM/WASND_BPH1/SCRIPT_PROPERTIES/properties Download the below files and make sure they exist in local server bph-RefIdAssertInfoCreatorImpl.properties bph-servergroups.props bph-serverusers.props bph-userregistry.properties fileRegistry.xml | 1 min | 20:18 | 20:19 | BPHTechnical Support Team
7 | PT-WASNDConfig-07 | Re-verfication of SSl and Security scripts | 1. config_bph1.properties 2. bph1_ssl_cert_maps.py 3 .bph1_sec_creation.py | 1 min | 20:19 | 20:20 | BPHTechnical Support Team
8 | PT-WASNDConfig-08 | Execution of SSL Cert maps script | Execute as per below instructions: for SSL script <> cd /usr/IBM/WASND_BPH1/WebSphere/ProcServer/bin/ ./wsadmin.sh -username admin -password password -language jython -f bph1_ssl_cert_maps.py | 10 mins | 20:20 | 20:30 | BPHTechnical Support Team
9 | PT-WASNDConfig-09 | Verify the files downloaded have required artefacts | Execute each command for each server(JVM) creation ./wsadmin.sh -username admin -password password -language jython -f PHSDEODServer01_creation.py ./wsadmin.sh -username admin -password password -language jython -f PHPJServer01_creation.py ./wsadmin.sh -username admin -password password -language jython -f PHGLSubmitServer01_creation.py ./wsadmin.sh -username admin -password password -language jython -f PHGLEventsServer01_creation.py ./wsadmin.sh -username admin -password password -language jython -f PHBWAServer01_creation.py ./wsadmin.sh -username admin -password password -language jython -f PHCPLCluster.py ./wsadmin.sh -username admin -password password -language jython -f PHDECluster.py ./wsadmin.sh -username admin -password password -language jython -f PHExecutionManagerCluster.py | 1.5 Hours | 20:30 | 22:00 | BPHTechnical Support Team
10 | PT-WASNDConfig-10 | Order of execution | The order should be as below: Install base version with Java 8 and apply their patches. Profile creations. SSL Configurations <<bph1_ssl_cert_maps.py >> Server creation <<*.py>> - Refer ID/Step# 9 BPH XA Datasource - Manually configure the Authentication Alias for XA Recovery(BPH), Component-Managed-Authentication Alias(BPH, Mapping Configuration Alias(none), container managed authentication alias(BPH) BPH XA Ref Datasource - Manually configure the Authentication Alias for XA Recovery(paymentref), Component-Managed-Authentication Alias(paymentref), Mapping Configuration Alias(none), container managed authentication alias(paymentref) JDBC connection should be tested Bounce all resources Ensure DMGR and Nodes are running. Start the application JVM and ensure it's up and running Stop Application JVM FIS recommended step to fix the sync issue <<./wsadmin.sh -conntype NONE -lang jacl -profile redeployFileTransfer.jacl -c "fileTransferAuthenticationOff auggvbpba802Cell01 auggvbpba802DMGRNode01 dmgr">> Restart DMGR Stop the node Sync the node Apply the security settings using the Jython script<< bph1_sec_creation.py>> Sync the Node Stop DMGR, Start DMGR and Start Node Install application Start JVM Run manual config script <<BPH_manual_config.py>> | 30 min | 22:00 | 22:30 | BPHTechnical Support Team
11 | PT-WASNDConfig-11 | Verifications of all configs | Login to Admin console and verify that all configurations are visible ServerDetails, SIT1Ports JVMPROPS, CommonAcrossQueues SSLConfig, INTQM, EXTQM, RTTMQM, MQBASENAMES, MQNAMES, MQDESCRIPTIONS BPHDBPROPS, BPHDBUserCreds, BPHAPPDBURL, ServerDetails, RefDBPROPS, RefDBUserCreds, RefAPPDBURL, CommonAcrossACTSPECS, ACTSPEC_createWMQActivationSpec, ACTSpecsTaskValues | 10 min | 22:30 | 22:40 | BPHTechnical Support Team
12 | PT-WASNDConfig-12 | Verifications of Ports | Login to Admin console , navigate to Application server and ports and verify that the ports are visible as given in the SIT1Ports section | 5 min | 22:40 | 22:45 | BPHTechnical Support Team
13 | PT-WASNDConfig-13 | Verifications of JVM Properties | Login to Admin console , navigate to Application server and then JVM properties to verify the JVM Props of Initial and maximum heap sizes | 2 min | 22:45 | 22:47 | BPHTechnical Support Team
14 | PT-WASNDConfig-14 | Verify the Datasources configurations | Navigate to Resources, JDBC and datasources to verify the configuratiosn to exists as given in the config file. | 2 min | 22:47 | 22:49 | BPHTechnical Support Team
15 | PT-WASNDConfig-15 | Verify the JDBC Provider configurations | Navigate to Resources, JDBC and JDBC Providers to verify the configuratiosn to exists as given in the config file. Verify the DB and RefDB parameters, 1. App Url 2. User Credentials 3. DB properties. | 5 min | 22:49 | 22:54 | BPHTechnical Support Team
16 | PT-WASNDConfig-16 | Verify the QCF configurations | Navigate to Resources, JMS, Que connection factories, to verity the configuratiosn to exists as given in the config file. | 2 min | 22:54 | 22:56 | BPHTechnical Support Team
17 | PT-WASNDConfig-17 | Verify the Queues configurations | Navigate to Resources, JMS, Queues, to verity the configuratiosn to exists as given in the config file. | 2 min | 22:56 | 22:58 | BPHTechnical Support Team

## RollBack
Roll back is not needed as this environment set up activity will not disturb existing env/application - New environment being set up in a new file system.
As this change is limited to installing the WASND9 and JDK 1.8 Packages there is no impact t to existing application in the existing BAU file system. In case of any issues in installing the packages the software's will be uninstalled and reinstalled under a new change request .
Confluence reference for software uninstalling and reinstalling the software's:
https://confluence.prod.cba/display/CPL/11.+Profiles+Deletion